## Burndown chart
[12 empty] | Robert | DataInterface and documentation |  |  | 2017-04-03 | 1 | 2
[12 empty] | Robert | Flink connection to ALE |  |  | 2017-04-13 | 6 | 0
| Date Cards Added: | [10 empty] | Kenneth | Parse Response data to something that can be used |  |  | 2017-04-14 | 16 | 0
| Data Interface | 2 | 2017-04-01 | [8 empty] | Greg | Landing Page |  |  | 2017-04-15 | 3 | 0
| ALE Automated Login | 16 | 2017-04-12 | [8 empty] | Dedre | Return location string via flink |  |  | 2017-04-16 | 2 | 2
| Parse response data to something that can be used | 8 | 2017-04-12 | [8 empty] | Tlou | ALE Automated Login |  |  | 2017-04-17 | 12 | 12
| Documentation | 3 | 2017-04-12 | [8 empty] | Pro | ALE Automated Login |  |  | 2017-04-17 | 12 | 12
| Flink connection to ALE | 8 | 2017-04-12 | [8 empty] | Tlou | ALE Automated Login |  |  | 2017-04-18 | 12 | 0
| Integration of ALE and DataInterface | 5 | 2017-04-12 | [8 empty] | Pro | ALE Automated Login |  |  | 2017-04-18 | 12 | 0
| Landing page | 5 | 2017-04-12 | [8 empty] | Pro | ALE Web Response in JSON format |  |  | 2017-04-18 | 6 | 1
| Format correct data for sending back | 8 | 2017-04-12 | [8 empty] | Greg | Format correct data for sending back |  |  | 2017-04-18 | 1 | 0
| Return location string via flink | 2 | 2017-04-16 | [8 empty] | Pro | ALE Web Response in JSON format |  |  | 2017-04-19 | 1 | 0
| Scrumboard/admin | 4 | 2017-04-17 | [8 empty] | Robert | Integration of ALE and DataInterface |  |  | 2017-04-19 | 4 | 0
| ALE Web Response JSON | 9 | 2017-04-18 | [8 empty] | Robert | Telnet server testing |  |  | 2017-04-19 | 1 | 0
| Setup maven | 3 | 2017-04-18 | [8 empty] | Pro | Documentation |  |  | 2017-04-19 | 2 | 1
| System testing | 1 | 2017-04-19 | [8 empty] | Greg | scrum board/admin |  |  | 2017-04-19 | 4 | 4
| Burndown chart | 2 | 2017-04-18 | [8 empty] | Greg | Burndown chart |  |  | 2017-04-19 | 2 | 2
[12 empty] | Dedre | Setup maven |  |  | 2017-04-20 | 6 | 0
[12 empty] | Dedre | Documentation |  |  | 2017-04-20 | 0.5 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 45 | 37 | 32 | 32 | 32 | 25 | 5 | 0
2017-04-01 | 2017-04-02 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | 2017-04-18 | 2017-04-19 | 2017-04-20
[11 empty] | 0 | 6 | 16 | 3 | 2 | 24 | 31 | 14 | 6.5
[11 empty] | 0 | 6 | 22 | 25 | 27 | 51 | 82 | 96 | 102.5
Burndown chart
Cumulative Hours Worked

## Scrumboard
S C R U M B O A R D
Todos and when they were added
2017-04-12 |  |  |  |  | TODO: | ETA | DateAdded
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done | Data Interface | 2 | 2017-04-01
Tasks | ETA | Task | ETA |  | ALE Automated Login | 16 | 2017-04-12
ALE Automated Login | 16 | Flink connection to ALE | 8 |  | Parse response data to something that can be used | 8 | 2017-04-12
Parse response data to something that can be used | 8 |  |  |  | Documentation | 3 | 2017-04-12
Documentation | 3 |  |  |  | Flink connection to ALE | 8 | 2017-04-12
Integration of ALE and DataInterface | 5 |  |  |  | Integration of ALE and DataInterface | 5 | 2017-04-12
Landing page | 5 |  |  |  | Landing page | 5 | 2017-04-12
Format correct data for sending back | 8 |  |  |  | Format correct data for sending back | 8 | 2017-04-12
[5 empty] | Return location string via flink | 2 | 2017-04-16
2017-04-13 |  |  |  |  | Scrumboard/admin | 4 | 2017-04-17
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done | ALE Web Response JSON | 9 | 2017-04-18
Tasks | ETA | Task | ETA |  | Setup maven | 3 | 2017-04-18
ALE Automated Login | 16 | Parse response data to something that can be used | 8 | Flink connection to ALE | System testing | 1 | 2017-04-19
Documentation | 3 | [5 empty] | 2017-04-18
Integration of ALE and DataInterface | 5
Landing page | 5 |  |  |  | Worklog
Format correct data for sending back | 8 |  |  |  |  | ETA
[5 empty] | DataInterface and documentation | 2 | 2017-04-03
2017-04-14 |  |  |  |  | Flink connection to ALE | 0 | 2017-04-13
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done | Parse Response data to something that can be used | 0 | 2017-04-14
Tasks | ETA | Task | ETA |  | Landing Page | 0 | 2017-04-15
ALE Automated Login | 16 |  |  | Flink connection to ALE | Return location string via flink | 2 | 2017-04-16
Documentation | 3 |  |  | Parse response data to something that can be used | ALE Automated Login | 12 | 2017-04-17
Integration of ALE and DataInterface | 5 |  |  |  | ALE Automated Login | 12 | 2017-04-17
Landing page | 5 |  |  |  | ALE Automated Login | 0 | 2017-04-18
Format correct data for sending back | 8 |  |  |  | ALE Automated Login | 0 | 2017-04-18
[5 empty] | ALE Web Response in JSON format | 1 | 2017-04-18
2017-04-15 |  |  |  |  | Format correct data for sending back | 0 | 2017-04-18
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done | ALE Web Response in JSON format | 0 | 2017-04-19 | ;
Tasks | ETA | Task | ETA |  | Integration of ALE and DataInterface | 0 | 2017-04-19 | ;
ALE Automated Login | 16 |  |  | Flink connection to ALE | Telnet server testing | 0 | 2017-04-19 | ;
Documentation | 3 |  |  | Parse response data to something that can be used | Documentation | 1 | 2017-04-19 | ;
Integration of ALE and DataInterface | 5 |  |  | Landing page | scrum board/admin | 0 | 2017-04-19 | ;
Format correct data for sending back | 8 |  |  |  | Burndown chart | 2 | 2017-04-19 | ;
2017-04-16 |  |  |  |  | Setup maven | 0 | 2017-04-20
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done | Documentation | 0 | 2017-04-20
Tasks | ETA | Task | ETA |  | Burndown chart | 0 | 2017-04-20
ALE Automated Login | 16 |  |  | Flink connection to ALE
Documentation | 3 |  |  | Parse response data to something that can be used
Integration of ALE and DataInterface | 5 |  |  | Landing page
Format correct data for sending back | 8 |  |  | Return location string via flink
2017-04-17
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
Documentation | 3 | ALE Automated Login | 12 | Flink connection to ALE
Integration of ALE and DataInterface | 5 |  |  | Parse response data to something that can be used
Format correct data for sending back | 8 |  |  | Landing page
Scrumboard/admin | 4 |  |  | Return location string via flink
2017-04-18
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
Documentation | 3 | ALE Web Response in JSON format | 1 | Flink connection to ALE
Integration of ALE and DataInterface | 5 |  |  | Parse response data to something that can be used
Scrumboard/admin | 4 |  |  | Landing page
Setup maven | 3 |  |  | Return location string via flink
Burndown chart | 2 |  |  | ALE Automated Login
Format correct data for sending back
2017-04-19
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
Setup maven | 3 | Documentation | 1 | Flink connection to ALE
|  | Burndown chart | 2 | Parse response data to something that can be used
Landing page
Return location string via flink
ALE Automated Login
ALE Web Response in JSON format
Format correct data for sending back
Integration of ALE and DataInterface
System testing
Scrumboard/admin
2017-04-20
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
Flink connection to ALE
Parse response data to something that can be used
Landing page
Return location string via flink
ALE Automated Login
ALE Web Response in JSON format
Format correct data for sending back
Integration of ALE and DataInterface
System testing
Scrumboard/admin
Setup maven
Documentation
Burndown chart