## Burndown chart
[12 empty] | Robert | DataInterface and documentation |  |  | 2017-04-03 | 1 | 2
[12 empty] | Robert | Flink connection to ALE |  |  | 2017-04-13 | 6 | 0
| Date Cards Added: | [10 empty] | Kenneth | Parse Response data to something that can be used |  |  | 2017-04-14 | 16 | 0
| Data Interface | 2 | 2017-04-01 | [8 empty] | Greg | Landing Page |  |  | 2017-04-15 | 3 | 0
| ALE Automated Login | 16 | 2017-04-12 | [8 empty] | Dedre | Return location string via flink |  |  | 2017-04-16 | 2 | 2
| Parse response data to something that can be used | 8 | 2017-04-12 | [8 empty] | Tlou | ALE Automated Login |  |  | 2017-04-17 | 12 | 12
| Documentation | 3 | 2017-04-12 | [8 empty] | Pro | ALE Automated Login |  |  | 2017-04-17 | 12 | 12
| Flink connection to ALE | 8 | 2017-04-12 | [8 empty] | Tlou | ALE Automated Login |  |  | 2017-04-18 | 12 | 0
| Integration of ALE and DataInterface | 5 | 2017-04-12 | [8 empty] | Pro | ALE Automated Login |  |  | 2017-04-18 | 12 | 0
| Landing page | 5 | 2017-04-12 | [8 empty] | Pro | ALE Web Response in JSON format |  |  | 2017-04-18 | 6 | 1
| Format correct data for sending back | 8 | 2017-04-12 | [8 empty] | Greg | Format correct data for sending back |  |  | 2017-04-18 | 1 | 0
| Return location string via flink | 2 | 2017-04-16 | [8 empty] | Pro | ALE Web Response in JSON format |  |  | 2017-04-19 | 1 | 0
| Scrumboard/admin | 4 | 2017-04-17 | [8 empty] | Robert | Integration of ALE and DataInterface |  |  | 2017-04-19 | 4 | 0
| ALE Web Response JSON | 9 | 2017-04-18 | [8 empty] | Robert | Telnet server testing |  |  | 2017-04-19 | 1 | 0
| Setup maven | 3 | 2017-04-18 | [8 empty] | Pro | Documentation |  |  | 2017-04-19 | 2 | 1
| System testing | 1 | 2017-04-19 | [8 empty] | Greg | scrum board/admin |  |  | 2017-04-19 | 4 | 4
| Burndown chart | 2 | 2017-04-18 | [8 empty] | Greg | Burndown chart |  |  | 2017-04-19 | 2 | 2
[12 empty] | Dedre | Setup maven |  |  | 2017-04-20 | 6 | 0
[12 empty] | Dedre | Documentation |  |  | 2017-04-20 | 0.5 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 45 | 37 | 32 | 32 | 32 | 25 | 5 | 0
2017-04-01 | 2017-04-02 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | 2017-04-18 | 2017-04-19 | 2017-04-20
[11 empty] | 0 | 6 | 16 | 3 | 2 | 24 | 31 | 14 | 6.5
[11 empty] | 0 | 6 | 22 | 25 | 27 | 51 | 82 | 96 | 102.5
Burndown chart
Cumulative Hours Worked

## Scrumboard
S C R U M B O A R D
Todos and when they were added
2017-04-12 | [5 empty] | TODO: | ETA | DateAdded
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done |  | Data Interface | 2 | 2017-04-01
Tasks | ETA | Task | ETA |  |  | ALE Automated Login | 16 | 2017-04-12
ALE Automated Login | 16 | Flink connection to ALE | 8 |  |  | Parse response data to something that can be used | 8 | 2017-04-12
Parse response data to something that can be used | 8 |  |  |  |  | Documentation | 3 | 2017-04-12
Documentation | 3 |  |  |  |  | Flink connection to ALE | 8 | 2017-04-12
Integration of ALE and DataInterface | 5 |  |  |  |  | Integration of ALE and DataInterface | 5 | 2017-04-12
Landing page | 5 |  |  |  |  | Landing page | 5 | 2017-04-12
Format correct data for sending back | 8 |  |  |  |  | Format correct data for sending back | 8 | 2017-04-12
[6 empty] | Return location string via flink | 2 | 2017-04-16
2017-04-13 | [5 empty] | Scrumboard/admin | 4 | 2017-04-17
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done |  | ALE Web Response JSON | 9 | 2017-04-18
Tasks | ETA | Task | ETA |  |  | Setup maven | 3 | 2017-04-18
ALE Automated Login | 16 | Parse response data to something that can be used | 8 | Flink connection to ALE | 0 | System testing | 1 | 2017-04-19
Documentation | 3 | [6 empty] | 2017-04-18
Integration of ALE and DataInterface | 5
Landing page | 5 |  |  |  |  | Worklog
Format correct data for sending back | 8 | [5 empty] | ETA
[6 empty] | DataInterface and documentation | 2 | 2017-04-03
2017-04-14 | [5 empty] | Flink connection to ALE | 0 | 2017-04-13
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done |  | Parse Response data to something that can be used | 0 | 2017-04-14
Tasks | ETA | Task | ETA |  |  | Landing Page | 0 | 2017-04-15
ALE Automated Login | 16 |  |  | Flink connection to ALE | 0 | Return location string via flink | 2 | 2017-04-16
Documentation | 3 |  |  | Parse response data to something that can be used | 0 | ALE Automated Login | 12 | 2017-04-17
Integration of ALE and DataInterface | 5 |  |  |  |  | ALE Automated Login | 12 | 2017-04-17
Landing page | 5 |  |  |  |  | ALE Automated Login | 0 | 2017-04-18
Format correct data for sending back | 8 |  |  |  |  | ALE Automated Login | 0 | 2017-04-18
[6 empty] | ALE Web Response in JSON format | 1 | 2017-04-18
2017-04-15 | [5 empty] | Format correct data for sending back | 0 | 2017-04-18
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done |  | ALE Web Response in JSON format | 0 | 2017-04-19 | ;
Tasks | ETA | Task | ETA |  |  | Integration of ALE and DataInterface | 0 | 2017-04-19 | ;
ALE Automated Login | 16 |  |  | Flink connection to ALE | 0 | Telnet server testing | 0 | 2017-04-19 | ;
Documentation | 3 |  |  | Parse response data to something that can be used | 0 | Documentation | 1 | 2017-04-19 | ;
Integration of ALE and DataInterface | 5 |  |  | Landing page | 0 | scrum board/admin | 0 | 2017-04-19 | ;
Format correct data for sending back | 8 |  |  |  |  | Burndown chart | 2 | 2017-04-19 | ;
2017-04-16 | [5 empty] | Setup maven | 0 | 2017-04-20
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done |  | Documentation | 0 | 2017-04-20
Tasks | ETA | Task | ETA |  |  | Burndown chart | 0 | 2017-04-20
ALE Automated Login | 16 |  |  | Flink connection to ALE | 0
Documentation | 3 |  |  | Parse response data to something that can be used | 0
Integration of ALE and DataInterface | 5 |  |  | Landing page | 0
Format correct data for sending back | 8 |  |  | Return location string via flink | 0
2017-04-17
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
Documentation | 3 | ALE Automated Login | 12 | Flink connection to ALE | 0
Integration of ALE and DataInterface | 5 |  |  | Parse response data to something that can be used | 0
Format correct data for sending back | 8 |  |  | Landing page | 0
Scrumboard/admin | 4 |  |  | Return location string via flink | 0
2017-04-18
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
Documentation | 3 | ALE Web Response in JSON format | 1 | Flink connection to ALE | 0
Integration of ALE and DataInterface | 5 |  |  | Parse response data to something that can be used | 0
Scrumboard/admin | 4 |  |  | Landing page | 0
Setup maven | 3 |  |  | Return location string via flink | 0
Burndown chart | 2 |  |  | ALE Automated Login | 0
|  |  |  | Format correct data for sending back | 0
2017-04-19
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
Setup maven | 3 | Documentation | 1 | Flink connection to ALE | 0
|  | Burndown chart | 2 | Parse response data to something that can be used | 0
|  |  |  | Landing page | 0
|  |  |  | Return location string via flink | 0
|  |  |  | ALE Automated Login | 0
|  |  |  | ALE Web Response in JSON format | 0
|  |  |  | Format correct data for sending back | 0
|  |  |  | Integration of ALE and DataInterface | 0
|  |  |  | System testing | 0
|  |  |  | Scrumboard/admin | 0
2017-04-20
Tasks TODO |  | Tasks in Progress and Testing |  | Tasks done
Tasks | ETA | Task | ETA
|  |  |  | Flink connection to ALE | 0
|  |  |  | Parse response data to something that can be used | 0
|  |  |  | Landing page | 0
|  |  |  | Return location string via flink | 0
|  |  |  | ALE Automated Login | 0
|  |  |  | ALE Web Response in JSON format | 0
|  |  |  | Format correct data for sending back | 0
|  |  |  | Integration of ALE and DataInterface | 0
|  |  |  | System testing | 0
|  |  |  | Scrumboard/admin | 0
|  |  |  | Setup maven | 0
|  |  |  | Documentation | 0
|  |  |  | Burndown chart | 0